## Sources and Uses of Funds USD
MOI UNIVERSITY
AFRICA HIGHER EDUCATION CENTERS OF EXCELLENCE PROJECT (151847)
Statement of Sources and Uses of Funds
for the semi-annual period ending……December 2017
|  | Semi-Annual Period ending…DEC 17… | Cummulative for Financial Year End
Sources of Fund
| Opening Cash Balance | $ | $
| Government Funds | 0 | 0
| World Bank IDA Funds | 0 | 0
| Student Fees | 0 | 0
| Others | 0 | 0
| Total | 0 | 0
Add Receipts
Government Funds
| World Bank IDA Funds | 1080823.2446 | 1080823.2446
| Student Fees | 837.8959 | 837.8959
| Others | 0 | 0
| Total Financing | 1081661.1404 | 1081661.1404
Less: ACE Expenditure as per Project Implementation Plan
1 | 1.0 Set-up institutional framework for commencement of the ACE | 80551.6223 | 80551.6223
2 | 2.0. Strengthen education capacity excellence - quality and productivity | 24233.9758 | 24233.9758
3 | 3.0 Education Capacity & Development Impact | 849.3947 | 849.3947
4 | 4.0 Strengthen Research Capacity excellence – quality and productivity | 81769.9177 | 81769.9177
5 | 5.0 Strengthen education and research capacity (through increased financial sustainability) and demonstration of value to students and partners | 0 | 0
6 | 6.0 Observation of best practices in ACE financial operation | 0 | 0
7 | 7.0 Observation of best practices in ACE procurement operation | 0 | 0
| Total Uses of Funds by Components | 187404.9104 | 187404.9104
| Closing Balances | 894256.23 | 894256.23
| Government Funds | 0
| World Bank IDA Funds | 893418.3341 | 893418.3341
| Student Fees | 837.8959 | 837.8959
| Others | 0
| Total Closing Cash Balance | 894256.23 | 894256.23
Prepared by Kirwa Chirchir
Accountant
Checked by Dr Rose Ramkat
Deputy CL
Approved by Prof Ambrose Kiprop
Center Leader

## Sources and Uses of Funds KSHS
MOI UNIVERSITY
AFRICA HIGHER EDUCATION CENTERS OF EXCELLENCE PROJECT (151847)
Statement of Sources and Uses of Funds
for the semi-annual period ending……December 2017
|  | Semi-Annual Period ending December 2017 | Cummulative for Financial Year End
Sources of Fund
| Opening Cash Balance | Kshs | Kshs
| Government Funds | 0 | 0
| World Bank IDA Funds | 0 | 0
| Student Fees | 0 | 0
| Others | 0 | 0
| Total | 0 | 0
Add Receipts
| Government Funds | 0
| World Bank IDA Funds | 111595000 | 111595000
| Student Fees | 86512.75 | 86512.75
| Others | 0 | 0
| Total Financing | 111681512.75 | 111681512.75
Less: ACE Expenditure as per Project Implementation Plan
1 | 1.0 Set-up institutional framework for commencement of the ACE | 8316955 | 8316955
2 | 2.0. Strengthen education capacity excellence - quality and productivity | 2502158 | 2502158
3 | 3.0 Education Capacity & Development Impact | 87700 | 87700
4 | 4.0 Strengthen Research Capacity excellence – quality and productivity | 8442744 | 8442744
5 | 5.0 Strengthen education and research capacity (through increased financial sustainability) and demonstration of value to students and partners | 0 | 0
6 | 6.0 Observation of best practices in ACE financial operation | 0 | 0
7 | 7.0 Observation of best practices in ACE procurement operation | 0 | 0
|  | 4925 | 4925
| Total Uses of Funds by Components | 19354482 | 19354482
| Closing Balances | 92327030.75 | 92327030.75
| Government Funds | 0 | 0
| World Bank IDA Funds | 92240518 | 92240518
| Student Fees | 86512.75 | 86512.75
| Others | 0 | 0
| Total Closing Cash Balance | 92327030.75 | 92327030.75
ds
Prepared by Kirwa Chirchir
Accountant
Checked by Dr Rose Ramkat
Deputy Center Leader
Approved by Prof Ambrose Kiprop
Center Leader

## Uses of Funds as per PIM USD
MOI UNIVERSITY
AFRICA HIGHER EDUCATION CENTERS OF EXCELLENCE PROJECT (151847)
Uses of Funds (Breakdown)
for the semi-annual period ending December 2017
USD
| Expenditure | Semi-Annual Period ending…DEC 17 |  |  | Cummulative for |  |  | Explanation of | PAD /Life of | Revised
[6 empty] | Financial Year End |  | Variance | Project | PAD
|  | Actual | Planned | Variance | Actual | Planned | Variance
| Expenditure Classification 1 as per Project Implementation Plan | $ | $ | $ | $ | $ | $
1 | 1.0 Set-up institutional framework for commencement of the ACE | 80551.6223 | 221500 | 140948.3777 | 80551.6223 | 221500 | 140948.3777
2 | 2.0. Strengthen education capacity excellence - quality and productivity | 24233.9758 | 137350 | 113116.0242 | 24233.9758 | 137350 | 113116.0242
3 | 3.0 Education Capacity & Development Impact | 849.3947 | 5000 | 4150.6053 | 849.3947 | 5000 | 4150.6053
4 | 4.0 Strengthen Research Capacity excellence – quality and productivity | 81769.9177 | 450356 | 368586.0823 | 81769.9177 | 450356 | 368586.0823
5 | 5.0 Strengthen education and research capacity (through increased financial sustainability) and demonstration of value to students and partners | 0 |  | 0 | 0 | 0 | 0
6 | 6.0 Observation of best practices in ACE financial operation | 0 |  | 0 | 0 | 0 | 0
7 | 7.0 Observation of best practices in ACE procurement operation | 0 |  | 0 | 0 | 0 | 0
| Sub Total | 187404.9104 | 814206 | 626801.0896 | 187404.9104 | 814206 | 626801.0896
1.0 Set-up institutional framework for commencement of the ACE
| 1.2.1 Drafting financial and procurement plans | 4180.1453 | 2000 | -2180.1453 | 4180.1453 | 2000 | -2180.1453
| 1.2.2 Drafting all standard operating procedures | 2265.3753 | 3000 | 734.6247 | 2265.3753 | 3000 | 734.6247
| 1.3.1Project inception workshop and official launch | 10612.9298 | 15000 | 4387.0702 | 10612.9298 | 15000 | 4387.0702
| 1.3.2Partners support to inception workshop | 5016.9492 | 6200 | 1183.0508 | 5016.9492 | 6200 | 1183.0508
| 1.4 Stakeholders workshop (community sensitization on project) | 3361.4528 | 3000 | -361.4528 | 3361.4528 | 3000 | -361.4528
1.5 Refurbish Centre Office Building
| 1.5.1 Refurbishing centre buildings | 0 | 110000 | 110000 | 0 | 110000 | 110000 | Delay in procurement; works started in the third quarter
| 1.5.2 Purchasing centre’s facilities and High performance Desktop PC (Apple iMac) | 15250.8959 | 50000 | 34749.1041 | 15250.8959 | 50000 | 34749.1041 | partlly done, High performance PC and other items in procurement process
1.6 Conduct seminars for self evaluation of project progress and industrial linkage committee meeting
| 1.6.3 Needs assessment for short courses, MSc course development in phytochemistry and one (1) baseline survey within Moi University | 6006.5375 | 8200 | 2193.4625 | 6006.5375 | 8200 | 2193.4625
| 1.6.4 Graduate tracer studies | 6006.5375 | 8000 | 1993.4625 | 6006.5375 | 8000 | 1993.4625
| 1.72 Progress report writing | 0 | 100 | 100 | 0 | 100 | 100
| 1.8.1 ACE meetings | 1090.5569 | 1000 | -90.5569 | 1090.5569 | 1000 | -90.5569
| 1.10 Cost for running ACE and other legible exercises not planned | 26760.2421 | 15000 | -11760.2421 | 26760.2421 | 15000 | -11760.2421 | Third quarter budget utulised
| Sub Total | 80551.6223 | 221500 | 140948.3777 | 80551.6223 | 221500 | 140948.3777
2.0. Strengthen education capacity excellence - quality and productivity
| 2.2 Advertisment of activities | 4067.7966 | 0 | -4067.7966 | 4067.7966 | 0 | -4067.7966 | Activity brought forward from third quarter
| 2.3.1 Lead partner support scholarships for national MSc students | 2542.3729 | 10000 | 7457.6271 | 2542.3729 | 10000 | 7457.6271 | Delay in Accreditation of programs by UIC led to delay in recruiting of students, activity to be undertaken in 3rd & 4th quarter
| 2.3.2 Lead partner support scholarships for regional MSc students | 0 | 5000 | 5000 | 0 | 5000 | 5000 | Delay in Accreditation of programs by UIC led to delay in recruiting of students, activity to be undertaken in 3rd & 4th quarter
| 2.3.3 National and Regional Partners support for MSc fellowships | 0 | 33920 | 33920 | 0 | 33920 | 33920 | Delay in Accreditation of programs by UIC led to delay in recruiting of students, activity to be undertaken in 3rd & 4th quarter
| 2.4 PhD Fellowships | [6 empty] | Delay in Accreditation of programs by UIC led to delay in recruiting of students, activity to be undertaken in 3rd & 4th quarter
| 2.4.1 Lead partner support scholarships for national PhD students | 0 | 14000 | 14000 | 0 | 14000 | 14000 | Delay in Accreditation of programs by UIC led to delay in recruiting of students, activity to be undertaken in 3rd & 4th quarter
| 2.4.2 Lead partner support scholarships for regional PhD students | 0 | 4000 | 4000 | 0 | 4000 | 4000 | Delay in Accreditation of programs by UIC led to delay in recruiting of students, activity to be undertaken in 3rd & 4th quarter
| 2.4.3 Support of partners towards PhD fellowships | 0 | 35000 | 35000 | 0 | 35000 | 35000 | Delay in Accreditation of programs by UIC led to delay in recruiting of students, activity to be undertaken in 3rd & 4th quarter
2.5 ICT Upgrading: , E-platforms establishment
| 2.5 ICT Upgrading: , E-platforms establishment | 7751.9613 | 0 | -7751.9613 | 7751.9613 | 0 | -7751.9613 | Activity brought forward
2.6 Re-tool faculty in areas relevant to the ACE curriculum delivery and supervision
| 2.6.1 Cost of material for training | 0 | 500 | 500 | 0 | 500 | 500 | Activity pushed forward to 3rd & 4th quarter
| 2.62 Logistics, venue, catering services | 0 | 3000 | 3000 | 0 | 3000 | 3000 | Activity pushed forward to 3rd & 4th quarter
| 2.63 Transport, accommodation & per diem of training facilitators for 3 days | 0 | 7000 | 7000 | 0 | 7000 | 7000 | Activity pushed forward to 3rd & 4th quarter
| 2.6.4 support partners to retool workshop | 0 | 3500 | 3500 | 0 | 3500 | 3500 | Activity pushed forward to 3rd & 4th quarter
| 2.7.2 Travel, accommodation, per diem, catering services on development of at least two (2) short courses | 0 | 3000 | 3000 | 0 | 3000 | 3000 | Activity pushed forward to 3rd & 4th quarter
| 2.9 Offer short courses and seminars | [6 empty] | Activity pushed forward to 3rd & 4th quarter
| 2.9.1 Material for use during short courses offering | 0 | 500 | 500 | 0 | 500 | 500 | Activity pushed forward to 3rd & 4th quarter
| 2.9.2 Travel, accommodation, per diem, catering services on development of at least two (2) short courses | 0 | 4500 | 4500 | 0 | 4500 | 4500 | Activity pushed forward to 3rd & 4th quarter
2.11 Institutional capcity development in governace,data system,leadership and monitoring and evaluation (leadership and Management workshop)
| 2.11.1 Catering services, logistics, venues, stationery, etc., for holding training | 2324.4552 | 2300 | -24.4552 | 2324.4552 | 2300 | -24.4552
| 2.11.2 Travel, accommodation, per diem for five facilitators/ consultants holding 3 days training | 764.1646 | 6000 | 5235.8354 | 764.1646 | 6000 | 5235.8354
| 2.11.3 support partners to leadership and management workshop | 6783.2252 | 5030 | -1753.2252 | 6783.2252 | 5030 | -1753.2252
| 2.11.4 stationary | 0 | 100 | 100 | 0 | 100 | 100
| Sub Total | 24233.9758 | 137350 | 113116.0242 | 24233.9758 | 137350 | 113116.0242
3.0 Education Capacity & Development Impact
| 3.1.1 Orientation /cultural seminars expense in terms of meals, transport, perdiem | 849.3947 | 1000 | 150.6053 | 849.3947 | 1000 | 150.6053
3.5 Visiting professors/external expertise
| 3.5.1 Support of professors/external expertise to PTRE (Travelling cost and Perdiem) | 0 | 3000 | 3000 | 0 | 3000 | 3000 | Delay due to industrial action by lectuers, pushed to last 2 quarters.
| 3.6.1 Travel, accommodation, per diem, catering services on development of at least 1 curriculum | 0 | 1000 | 1000 | 0 | 1000 | 1000 | Delay due to industrial action by lectuers, pushed to last 2 quarters.
| Sub Total | 849.3947 | 5000 | 4150.6053 | 849.3947 | 5000 | 4150.6053
4.0 Strengthen Research Capacity excellence – quality and productivity
| 4.1 Upgrade of of Textile labaratory and Phytochemical research labaratory ,renewable energy and generator back up | 0 | 328656 | 328656 | 0 | 328656 | 328656 | Procurement challenges, works stared in 3rd quarter
| 4.4.1 Laboratory consumables (textile materials, chemicals reagents, safety clothing, glassware) | 0 | 10000 | 10000 | 0 | 10000 | 10000 | Procurement challenges, works stared in 3rd quarter
| 4.7.1 .Support of faculty and ACE team to establish Memorundum of Understandings with partners (Travelling cost and Perdiem) | 3065.1332 | 10000 | 6934.8668 | 3065.1332 | 10000 | 6934.8668 | Task partly complete
| 4.8.1 Support of staff mobility to public and private sector institutions of higher learning and industry (Travelling cost and Perdiem) | 3448.6102 | 10000 | 6551.3898 | 3448.6102 | 10000 | 6551.3898 | Task partly complete
| 4.9.1 Grant application logistics (Travel, Perdiem, communication, stationeries, venues, consultancy cost) | 0 | 3000 | 3000 | 0 | 3000 | 3000 | Task partly complete,
| 4.12.1 Professional skills training and conference attendance logistics (Travel, Perdiem, communication, stationeries, publication, visas, insurance ) | 0 | 5000 | 5000 | 0 | 5000 | 5000 | Activity postponed funds to be utulised in 3rd & 4th quarter
| 4.12.2 Support partners to seminar workshop, conference and short courses | 0 | 1200 | 1200 | 0 | 1200 | 1200 | vehicle insurance to be paid in 3rd quarter
| 4.14.3 Vehicle Insurance – 4x4 extended land cruiser | 0 | 2000 | 2000 | 0 | 2000 | 2000 | vehicle received at end of 2nd quarter, funds to be utulised in subsequenr period
| 4.14.4 Vehicle service and maintenance – 4x4 land cruiser | 0 | 500 | 500 | 0 | 500 | 500 | vehicle received at end of 2nd quarter, funds to be utulised in subsequenr period
| 4.14.5 Local and regional travel (Fuel and Perdiem) | 0 | 2000 | 2000 | 0 | 2000 | 2000 | vehicle received at end of 2nd quarter
| 4.16.1 Purchase of one 4x4 extended double cabin pick-up | 71670.7022 | 74000 | 2329.2978 | 71670.7022 | 74000 | 2329.2978 | reasonable variance, purchase price negotiated downwards
| 4.18.1 Support for training i.e fees for course, perdiem, transport, air ticket) | 3585.4722 | 4000 | 414.5278 | 3585.4722 | 4000 | 414.5278
| Sub Total | 81769.9177 | 450356 | 368586.0823 | 81769.9177 | 450356 | 368586.0823
| Grand Total Uses of Funds | 187404.9104 | 814206 | 626801.0896 | 187404.9104 | 814206 | 626801.0896
NOTE: CURRENCY CONVERSION RATE USED IS 1USD = KSH. 103.25
Prepared by Kirwa Chirchir
Accountant
Checked by Dr Rose Ramkat
Deputy CL
Approved by Prof Ambrose Kiprop
Center Leader

## Uses of Funds as per PIM KSH
MOI UNIVERSITY
AFRICA HIGHER EDUCATION CENTERS OF EXCELLENCE PROJECT (151847)
Uses of Funds (Breakdown)
for the semi-annual period ending December 2017
| Expenditure | Semi-Annual Period ending…DEC 17 |  |  | Cummulative for |  |  | Explanation of | PAD /Life of | Revised
[6 empty] | Financial Year End |  | Variance | Project | PAD
|  | Actual | Planned | Variance | Actual | Planned | Variance
| Expenditure Classification 1 as per Project Implementation Plan | Kshs | Kshs | Kshs | Kshs | Kshs | Kshs
1 | 1.0 Set-up institutional framework for commencement of the ACE | 8316955 | 22869875 | 14552920 | 8316955 | 22869875 | 14552920
2 | 2.0. Strengthen education capacity excellence - quality and productivity | 2502158 | 14181387.5 | 11679229.5 | 2502158 | 14181387.5 | 11679229.5
3 | 3.0 Education Capacity & Development Impact | 87700 | 516250 | 428550 | 87700 | 516250 | 428550
4 | 4.0 Strengthen Research Capacity excellence – quality and productivity | 8442744 | 46499257 | 38056513 | 8442744 | 46499257 | 38056513
5 | 5.0 Strengthen education and research capacity (through increased financial sustainability) and demonstration of value to students and partners | 0 | 0 | 0 | 0 | 0 | 0
6 | 6.0 Observation of best practices in ACE financial operation | 0 | 0 | 0 | 0 | 0 | 0
7 | 7.0 Observation of best practices in ACE procurement operation | 0 | 0 | 0 | 0 | 0 | 0
| Sub Total | 19349557 | 84066769.5 | 64717212.5 | 19349557 | 84066769.5 | 64717212.5
1.0 Set-up institutional framework for commencement of the ACE
| 1.2.1 Drafting financial and procurement plans | 431600 | 206500 | -225100 | 431600 | 206500 | -225100
| 1.2.2 Drafting all standard operating procedures | 233900 | 309750 | 75850 | 233900 | 309750 | 75850
| 1.3.1Project inception workshop and official launch | 1095785 | 1548750 | 452965 | 1095785 | 1548750 | 452965
| 1.3.2Partners support to inception workshop | 518000 | 640150 | 122150 | 518000 | 640150 | 122150
| 1.4 Stakeholders workshop (community sensitization on project) | 347070 | 309750 | -37320 | 347070 | 309750 | -37320
1.5 Refurbish Centre Office Building
| 1.5.1 Refurbishing centre buildings | 0 | 11357500 | 11357500 | 0 | 11357500 | 11357500 | Delay in procurement; works started in the third quarter
| 1.5.2 Purchasing centre’s facilities and High performance Desktop PC (Apple iMac) | 1574655 | 5162500 | 3587845 | 1574655 | 5162500 | 3587845 | partlly done, High performance PC and other items in procurement process
1.6 Conduct seminars for self evaluation of project progress and industrial linkage committee meeting
| 1.6.3 Needs assessment for short courses, MSc course development in phytochemistry and one (1) baseline survey within Moi University | 620175 | 846650 | 226475 | 620175 | 846650 | 226475
| 1.6.4 Graduate tracer studies | 620175 | 826000 | 205825 | 620175 | 826000 | 205825
| 1.72 Progress report writing | 0 | 10325 | 10325 | 0 | 10325 | 10325
| 1.8.1 ACE meetings | 112600 | 103250 | -9350 | 112600 | 103250 | -9350
| 1.10 Cost for running ACE and other legible exercises not planned | 2762995 | 1548750 | -1214245 | 2762995 | 1548750 | -1214245 | Third quarter budget utulised
| Sub Total | 8316955 | 22869875 | 14552920 | 8316955 | 22869875 | 14552920
2.0. Strengthen education capacity excellence - quality and productivity
| 2.2 Advertisment of activities | 420000 | 0 | -420000 | 420000 | 0 | -420000 | Activity brought forward from third quarter
| 2.3.1 Lead partner support scholarships for national MSc students | 262500 | 1032500 | 770000 | 262500 | 1032500 | 770000 | Delay in Accreditation of programs by UIC led to delay in recruiting of students, activity to be undertaken in 3rd & 4th quarter
| 2.3.2 Lead partner support scholarships for regional MSc students | 0 | 516250 | 516250 | 0 | 516250 | 516250 | Delay in Accreditation of programs by UIC led to delay in recruiting of students, activity to be undertaken in 3rd & 4th quarter
| 2.3.3 National and Regional Partners support for MSc fellowships | 0 | 3502240 | 3502240 | 0 | 3502240 | 3502240 | Delay in Accreditation of programs by UIC led to delay in recruiting of students, activity to be undertaken in 3rd & 4th quarter
| 2.4 PhD Fellowships | [6 empty] | Delay in Accreditation of programs by UIC led to delay in recruiting of students, activity to be undertaken in 3rd & 4th quarter
| 2.4.1 Lead partner support scholarships for national PhD students | 0 | 1445500 | 1445500 | 0 | 1445500 | 1445500 | Delay in Accreditation of programs by UIC led to delay in recruiting of students, activity to be undertaken in 3rd & 4th quarter
| 2.4.2 Lead partner support scholarships for regional PhD students | 0 | 413000 | 413000 | 0 | 413000 | 413000 | Delay in Accreditation of programs by UIC led to delay in recruiting of students, activity to be undertaken in 3rd & 4th quarter
| 2.4.3 Support of partners towards PhD fellowships | 0 | 3613750 | 3613750 | 0 | 3613750 | 3613750 | Delay in Accreditation of programs by UIC led to delay in recruiting of students, activity to be undertaken in 3rd & 4th quarter
2.5 ICT Upgrading: , E-platforms establishment
| 2.5 ICT Upgrading: , E-platforms establishment | 800390 | 0 | -800390 | 800390 | 0 | -800390 | Activity brought forward
2.6 Re-tool faculty in areas relevant to the ACE curriculum delivery and supervision
| 2.6.1 Cost of material for training | 0 | 51625 | 51625 | 0 | 51625 | 51625 | Activity pushed forward to 3rd & 4th quarter
| 2.62 Logistics, venue, catering services | 0 | 309750 | 309750 | 0 | 309750 | 309750 | Activity pushed forward to 3rd & 4th quarter
| 2.63 Transport, accommodation & per diem of training facilitators for 3 days | 0 | 722750 | 722750 | 0 | 722750 | 722750 | Activity pushed forward to 3rd & 4th quarter
| 2.6.4 support partners to retool workshop | 0 | 361375 | 361375 | 0 | 361375 | 361375 | Activity pushed forward to 3rd & 4th quarter
| 2.7.2 Travel, accommodation, per diem, catering services on development of at least two (2) short courses | 0 | 309750 | 309750 | 0 | 309750 | 309750 | Activity pushed forward to 3rd & 4th quarter
| 2.9 Offer short courses and seminars | [6 empty] | Activity pushed forward to 3rd & 4th quarter
| 2.9.1 Material for use during short courses offering | 0 | 51625 | 51625 | 0 | 51625 | 51625 | Activity pushed forward to 3rd & 4th quarter
| 2.9.2 Travel, accommodation, per diem, catering services on development of at least two (2) short courses | 0 | 464625 | 464625 | 0 | 464625 | 464625 | Activity pushed forward to 3rd & 4th quarter
2.11 Institutional capcity development in governace,data system,leadership and monitoring and evaluation (leadership and Management workshop)
| 2.11.1 Catering services, logistics, venues, stationery, etc., for holding trainin | 240000 | 237475 | -2525 | 240000 | 237475 | -2525
| 2.11.2 Travel, accommodation, per diem for five facilitators/ consultants holding 3 days training | 78900 | 619500 | 540600 | 78900 | 619500 | 540600
| 2.11.3 support partners to leadership and management workshop | 700368 | 519347.5 | -181020.5 | 700368 | 519347.5 | -181020.5
| 2.11.4 stationary | 0 | 10325 | 10325 | 0 | 10325 | 10325
| Sub Total | 2502158 | 14181387.5 | 11679229.5 | 2502158 | 14181387.5 | 11679229.5
3.0 Education Capacity & Development Impact
| 3.1.1 Orientation /cultural seminars expense in terms of meals, transport, perdiem | 87700 | 103250 | 15550 | 87700 | 103250 | 15550
3.5 Visiting professors/external expertise
| 3.5.1 Support of professors/external expertise to PTRE (Travelling cost and Perdiem) | 0 | 309750 | 309750 | 0 | 309750 | 309750 | Delay due to industrial action by lectuers, pushed to last 2 quarters.
| 3.6.1 Travel, accommodation, per diem, catering services on development of at least 1 curriculum | 0 | 103250 | 103250 | 0 | 103250 | 103250 | Delay due to industrial action by lectuers, pushed to last 2 quarters.
| Sub Total | 87700 | 516250 | 428550 | 87700 | 516250 | 428550
4.0 Strengthen Research Capacity excellence – quality and productivity
| 4.1 Upgrade of of Textile labaratory and Phytochemical research labaratory ,renewable energy and generator back up | 0 | 33933732 | 33933732 | 0 | 33933732 | 33933732 | Procurement challenges, works stared in 3rd quarter
| 4.4.1 Laboratory consumables (textile materials, chemicals reagents, safety clothing, glassware) | 0 | 1032500 | 1032500 | 0 | 1032500 | 1032500 | Procurement challenges, works stared in 3rd quarter
| 4.7.1 .Support of faculty and ACE team to establish Memorundum of Understandings with partners (Travelling cost and Perdiem) | 316475 | 1032500 | 716025 | 316475 | 1032500 | 716025 | Task partly complete
| 4.8.1 Support of staff mobility to public and private sector institutions of higher learning and industry (Travelling cost and Perdiem) | 356069 | 1032500 | 676431 | 356069 | 1032500 | 676431 | Task partly complete
| 4.9.1 Grant application logistics (Travel, Perdiem, communication, stationeries, venues, consultancy cost) | 0 | 309750 | 309750 | 0 | 309750 | 309750 | Task partly complete,
| 4.12.1 Professional skills training and conference attendance logistics (Travel, Perdiem, communication, stationeries, publication, visas, insurance ) | 0 | 516250 | 516250 | 0 | 516250 | 516250 | Activity postponed funds to be utulised in 3rd & 4th quarter
| 4.12.2 Support partners to seminar workshop, conference and short courses | 0 | 123900 | 123900 | 0 | 123900 | 123900 | Activity postponed funds to be utulised in 3rd & 4th quarter
| 4.14.3 Vehicle Insurance – 4x4 extended land cruiser | 0 | 206500 | 206500 | 0 | 206500 | 206500 | vehicle insurance to be paid in 3rd quarter
| 4.14.4 Vehicle service and maintenance – 4x4 land cruiser | 0 | 51625 | 51625 | 0 | 51625 | 51625 | vehicle received at end of 2nd quarter, funds to be utulised in subsequenr period
| 4.14.5 Local and regional travel (Fuel and Perdiem) | 0 | 206500 | 206500 | 0 | 206500 | 206500 | vehicle received at end of 2nd quarter, funds to be utulised in subsequenr period
| 4.16.1 Purchase of one 4x4 extended double cabin pick-up | 7400000 | 7640500 | 240500 | 7400000 | 7640500 | 240500 | reasonable variance, purchase price negotiated downwards
| 4.18.1 Support for training i.e fees for course, perdiem, transport, air ticket) | 370200 | 413000 | 42800 | 370200 | 413000 | 42800
| Sub Total | 8442744 | 46499257 | 38056513 | 8442744 | 46499257 | 38056513
| Grand Total Uses of Funds | 19349557 | 84066769.5 | 64717212.5 | 19349557 | 84066769.5 | 64717212.5
NOTE: CURRENCY CONVERSION RATE USED IS 1USD = KSH. 103.25
Prepared by Kirwa Chirchir
Accountant
Checked by Dr Rose Ramkat
Deputy CL
Approved by Prof Ambrose Kiprop
Center Leader

## EEP Statement Kshs
MOI UNIVERSITY AFRICA HIGHER EDUCATION CENTERS OF EXCELLENCE PROJECT (151847)
Statement of Reimbursable Eligible Expenditure Programs (EEPs)
for the semi-annual period ending December 2017
Eligible Expenditure Program (EEP)
| Kshs | Kshs
EEP 1: Salaries | 2098899760 | 2098899760
EEP 2: Non Procurable Expenditure as defined in Financing Agreement | 0 | 0
Total EEPs | 2098899760 | 2098899760

## EEP Statement USD)
MOI UNIVERSITY AFRICA HIGHER EDUCATION CENTERS OF EXCELLENCE PROJECT (151847)
Statement of Reimbursable Eligible Expenditure Programs (EEPs)
for the semi-annual period ending December 2017
| Semi-Annual Period ending…Dec 2017… | Cummulative for Financial Year End
Eligible Expenditure Program (EEP)
| $ | $
EEP 1: Salaries | 20328326.9734 | 20328326.9734
EEP 2: Non Procurable Expenditure as defined in Financing Agreement | 0 | 0
Total EEPs | 20328326.9734 | 20328326.9734

## DLI Statement
MOI UNIVERSITY
AFRICA HIGHER EDUCATION CENTERS OF EXCELLENCE PROJECT (151847)
NOTES ANNEX
DISBURSEMENT LINKED TO INDICATORS | ACTIONS TO BE COMPLETED | STATUS OF ACTIONS COMPLETION | AMOUNT ALLOCATED(USD) | AMOUNT DISBURSED(USD) | UNDISBURSED BALANCE (USD)
DLI1: Institutional Readiness | DLR#1.1: To meet Conditions for effectiveness Creation of ACE designated account. Approved Financial Management and procurement procedures and Environmental and social management palns capacity. | completed | 600000 | 600000 | Nil
| DLR#1.2: Development of detailed implmentation plans. Signing of funding and performance contract between the University and the Governfment. | completed | 500000 | 500000 | Nil
DLI2 | DLR# 2.1: Timely annual implementation of the plans | Ongoing | 500000 | Nil | 500000
Excellence in education and research capacity and development impact | At least 70% of the annual activities achieved
| DLR #2.2: Newly enrolled students in the ACE of which at least 20% must be regional (African) students. | 29 students enrolled under ACE II PTRE | 1200000 | Nil | 1200000
| DLR#2.3: Accreditation of quality of education programs | 3 programmes accreditted by CUE | 600000 | Nil | 600000
| DLR#2.4: Collaboration and partnerships for applied research and training. Signing of the partnership MOUs for at least a period of two years | 1 MOU developed and signed with a private partner NORCART International | 200000 | Nil | 200000
| DLR#2.5: Peer-reviewed journal papers or peer-reviewed conference papers prepared collaboratively with regionally or international partners | 1 conference paper published with a regional partner | 300000 | Nil | 300000
| DLR#2.6: Faculty and PhD student exchanges to promote regional research and teaching | Faculty exchange in Gezira University | 500000 | Nil | 500000
| DLR#2.7: External revenue generation | Students application fee | 900000 | Nil | 900000
| DLR#2.8: Institution participating in benchmarking exercise | Ongoing | 100000 | Nil | 100000
DLI3 | DLR#3.1: Timely Withdrawal Application supported by financial reporting on the ACE account for the period | Not yet | 75000 | Nil | 75000
Timely, transparent and institutionally reviewed Financial Management | DLR#3.2: Functioning Audit Committee under the university council | In Place | 75000 | Nil | 75000
| DLR#3.3: Functioning internal audit unit for the university. Internal audit unit in place | In Place | 75000 | Nil | 75000
| DLR#3.4: Transparency of financial management (audit reports, interim financial reports, budgets and annual work plan are all web accessible) | Procurement Plan accessible in the University Website Ongoing | 75000 | Nil | 75000
DLI4 | DLR# 4.1 Timely procurement audit report | Ongoing | 150000 | Nil | 150000
Timely and audited procurement | Timely submission of procurement audit report
| DLR#4.2: Timely and satisfactory procurement progress report | Ongoing | 150000 | Nil | 150000
Timely submission of procurement progress report

## ACTIVITIES
MOI UNIVERSITY
AFRICA CENTRE OF EXCELLENCE (ACE II)
BUDGET FOR 1ST & 2ND QUARTER; JULY- DEC 2017
NO. | ITEM/SERVICE | FUNDS | TIMING OF ACTIVITIES |  |  |  | TOTALS
| DESCRIPTION | ALLOCATED | 2017/2018 1ST | 2017/2018 2ND | 2017/2018 3RD | 2017/2018 4TH |  | Component total ACE LEADER | (Component total partners) | PAYMENTS JULY-DEC 17
|  | IN USD. | QUARTER | QUARTER | QUARTER | QUARTER |  |  |  | PAID - Kshs | COMMITTED | TOTAL Kshs | under / (over) spend kshs | % usage
|  |  | JUL-SEP | OCT-DEC | JAN-MAR | APRIL-JULY
1.2 | Put in place operational manual for ACE administration,: procurement, financial management, independent evaluation committee for award of scholarships and research grants, monitoring and evaluation (standard operating procedures)
1.2.1 | Drafting financial and procurement plans | 2000 | 2000 | 0 | 0 | 0 | 2000 | 2000 | 0 | 431600 |  | 431600 | -228700
1.2.2 | Drafting all standard operating procedures | 3000 | 3000 | 0 | 0 | 0 | 3000 | 3000 | 0 | 233900 |  | 233900 | 70450
| SUB-TOTALS | 5000 | 5000 | 0 | 0 | 0 | 5000 | 5000 | 0 | 665500 | 0 | 665500 | -158250 | 131.2%
1.3 | ACE Implementation team meeting on world bank procedures
1.3.1 | Project inception workshop and official launch | 15000 | 15000 | 0 | 0 | 0 | 15000 | 15000 | 0 | 1095785 |  | 1095785 | 425965
1.3.2 | Partners support to inception workshop | 6200 | 6200 | 0 | 0 | 0 | 6200 | 0 | 6200 | 518000 |  | 518000 | 110990
| SUB-TOTALS | 21200 | 21200 | 0 | 0 | 0 | 21200 | 15000 | 6200 | 1613785 | 0 | 1613785 | 536955 | 75.03%
1.4 | Community and stakeholders sensitization | [11 empty] | 0
1.4.2 | Stakeholders workshop (community sensitization on project) | 3000 |  | 3000 | 0 | 0 | 3000 | 3000 | 0 | 347070 | 0 | 347070 | -42720
| SUB-TOTAL | 3000 | 0 | 3000 | 0 | 0 | 3000 | 3000 | 0 | 347070 | 0 | 347070 | -42720 | 115.7%
1.5 | Refurbish Centre Office Building | [10 empty] | 0 | 0
1.5.1 | Refurbishing centre buildings | 110000 | 0 | 110000 | 0 | 0 | 110000 | 110000 | 0 |  |  | 0 | 11159500
1.5.2 | Purchasing centre’s facilities and High performance Desktop PC (Apple iMac) | 50000 | 0 | 50000 | 0 | 0 | 50000 | 50000 | 0 | 1574655 | 0 | 1574655 | 3497845
| SUB-TOTAL | 160000 | 0 | 160000 | 0 | 0 | 160000 | 160000 | 0 | 1574655 | 0 | 1574655 | 14657345 | 9.701%
1.6 | Conduct seminars for self evaluation of project progress and industrial linkage committee meeting
1.6.1 | Self-evaluation seminars | 10000 | 0 | 0 | 0 | 10000 | 10000 | 10000 | 0 |  |  | 0 | 0
1.6.2 | Industrial committee meeting | 2000 | 0 | 0 | 2000 | 0 | 2000 | 2000 | 0 |  |  | 0 | 0
1.6.3 | Needs assessment for short courses, MSc course development in phytochemistry and one (1) baseline survey within Moi University | 8200 | 0 | 8200 | 0 | 0 | 8200 | 8200 | 0 | 620175 |  | 620175 | 211715
1.6.4 | Graduate tracer studies | 8000 | 0 | 8000 | 0 | 0 | 8000 | 8000 | 0 | 620175 |  | 620175 | 191425
| SUB-TOTAL | 28200 | 0 | 16200 | 2000 | 10000 | 28200 | 28200 | 0 | 1240350 | 0 | 1240350 | 403140 | 75.47%
1.7 | Collecting and analyzing data for technical reporting and M&E on education and research
1.7.1 | Course Evaluation and data analysis | 100 | 0 | 0 | 0 | 100 | 100 | 100 | 0 |  |  | 0 | 0
1.7.2 | Progress report writing | 200 | 50 | 50 | 50 | 50 | 200 | 200 | 0 |  |  | 0 | 10145
| SUB-TOTAL | 300 | 50 | 50 | 50 | 150 | 300 | 300 | 0 | 0 | 0 | 0 | 10145 | 0%
1.8 | Plan and hold ACE implementation meetings
1.8.1 | ACE meetings | 2000 | 500 | 500 | 500 | 500 | 2000 | 2000 | 0 | 112600 |  | 112600 | -11150
| SUB-TOTAL | 2000 | 500 | 500 | 500 | 500 | 2000 | 2000 | 0 | 112600 | 0 | 112600 | -11150 | 111%
1.1 | ACE Operation Cost
1.1 | Cost for running ACE and other legible exercises not planned | 44000 | 5000 | 10000 | 10000 | 19000 | 44000 | 44000 | 0 | 2762995 | 0 | 2762995 | -1241245
| SUB-TOTAL | 44000 | 5000 | 10000 | 10000 | 19000 | 44000 | 44000 | 0 | 2762995 | 0 | 2762995 | -1241245 | 181.6%
| TOTAL ACTIVITY 1 | 263700 | 31750 | 189750 | 12550 | 29650 | 263700 |  |  | 8316955 | 0 | 8316955 | 14154220 | 37.01% | `
2.1 | Gender sensitization on postgraduate training in the areas of stem
2.1.1 | Travel, accommodation, per diem for three facilitators holding two career /open days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1.2 | Catering services, logistics, venues, stationery, etc., for holding career/open days and information campaigns | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| SUB-TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2 | Advertisment of activities
2.2.1 | Advertisement of ACE postgraduate programs in print media (i.e., local newspapers, brochures,posters, etc.) | 5000 | 0 | 0 | 5000 | 0 | 5000 | 5000 | 0 | 420000 |  | 420000 | -420000
| SUB-TOTAL | 5000 | 0 | 0 | 5000 | 0 | 5000 | 5000 | 0 | 420000 | 0 | 420000 | -420000
2.3 | MSc Fellowships
2.3.1 | Lead partner support scholarships for national MSc students | 16600 | 0 | 10000 | 6600 | 0 | 16600 | 16600 | 0 | 262500 |  | 262500 | 752000 | 25.87%
2.3.2 | Lead partner support scholarships for regional MSc students | 5325 | 0 | 5000 | 325 | 0 | 5325 | 5325 | 0 |  |  | 0 | 507250
2.3.3 | National and Regional Partners support for MSc fellowships | 53920 | 0 | 33920 | 10000 | 10000 | 53920 | 0 | 53920 | 0 |  | 0 | 3441184
| SUB-TOTAL | 75845 | 0 | 48920 | 16925 | 10000 | 75845 | 21925 | 53920 | 262500 | 0 | 262500 | 4700434 | 5.289%
2.4 | PhD Fellowships
2.4.1 | Lead partner support scholarships for national PhD students | 13800 | 0 | 14000 | 10600 | 10000 | 34600 | 13800 | 0 |  |  | 0 | 1420300
2.4.2 | Lead partner support scholarships for regional PhD students | 0 | 0 | 4000 | 1000 | 380 | 5380 | 0 | 0 |  |  | 0 | 405800
2.4.3 | Support of partners towards PhD fellowships | 80100 | 0 | 35000 | 10000 | 8920 | 53920 | 0 | 80100 |  |  | 0 | 3550750
| SUB-TOTAL | 93900 | 0 | 53000 | 21600 | 19300 | 93900 | 13800 | 80100 | 0 | 0 | 0 | 5376850 | 0%
2.5 | ICT Upgrading: , E-platforms establishment
2.5.1 | Installation of projectors in teaching rooms, Smart/Interactive white boards, & development of a teleconferencing room | 21000 | 0 | 0 | 21000 | 0 | 21000 | 21000 | 0 |  |  | 0 | 0
2.5.2 | Development/Adoption of E-learning Platform | 1000 | 0 | 0 | 1000 | 0 | 1000 | 1000 | 0 |  |  | 0 | 0
2.5.3 | Provision of Internet connectivity (Accessories for linking to the university backbone) | 2000 | 0 | 0 | 2000 | 0 | 2000 | 2000 | 0 |  |  | 0 | 0
2.5.4 | Setting up a Local Area Network (LAN) in offices (2) and one ICT/Computer lab, &Wi-Fi connectivity within the Center | 3400 | 0 | 0 | 3400 | 0 | 3400 | 3400 | 0 |  |  | 0 | 0
2.5.5 | Increase Internet Bandwidth (20 Mbps) | 7000 | 0 | 0 | 7000 | 0 | 7000 | 7000 | 0 |  |  | 0 | 0
2.5.6 | Purchase projectors, laptops, scanners,printers, & photocopiers with scanning and network printing facility | 14600 | 0 | 0 | 14600 | 0 | 14600 | 14600 | 0 | 800390 |  | 800390 | -800390
2.5.7 | Interactive Website for research dissemination | 1000 | 0 | 0 | 1000 | 0 | 1000 | 1000 | 0 |  |  | 0 | 0
2.5.8 | Training users on use of e-learning platform | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| SUB-TOTAL | 50000 | 0 | 0 | 50000 | 0 | 50000 | 50000 | 0 | 800390 | 0 | 800390 | -800390
2.6 | Re-tool faculty in areas relevant to the ACE curriculum delivery and supervision
2.6.1 | Cost of material for training | 500 | 0 | 500 | 0 | 0 | 500 | 500 | 0 |  |  | 0 | 50725
2.6.2 | Logistics, venue, catering services | 3000 | 0 | 3000 | 0 | 0 | 3000 | 3000 | 0 |  |  | 0 | 304350
2.6.3 | Transport, accommodation & per diem of training facilitators for 3 days | 7000 | 0 | 7000 | 0 | 0 | 7000 | 7000 | 0 |  |  | 0 | 710150
2.6.4 | support partners to retool workshop | 3500 |  | 3500 | 0 |  | 3500 | 0 | 3500 |  |  | 0 | 355075
| SUB-TOTAL | 14000 | 0 | 14000 | 0 | 0 | 14000 | 10500 | 3500 | 0 | 0 | 0 | 1420300
2.7 | Develop short courses curricullum
2.7.1 | Material for development of short courses | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.7.2 | Travel, accommodation, per diem, catering services on development of at least two (2) short courses | 6500 | 0 | 3000 | 3500 | 6500 | 6500 | 6500 | 0 |  |  | 0 | 304350
| SUB-TOTAL | 6500 | 0 | 3000 | 3500 | 6500 | 6500 | 6500 | 0 | 0 | 0 | 0 | 304350
2.9 | Offer short courses and seminars | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
2.9.1 | Material for use during short courses offering | 1500 |  | 500 | 500 | 500 | 1500 | 1500 | 0 |  |  | 0 | 50725
2.9.2 | Travel, accommodation, per diem, catering services on development of at least two (2) short courses | 13500 |  | 4500 | 4500 | 4500 | 13500 | 13500 | 0 |  |  | 0 | 456525
| SUB-TOTAL | 15000 | 0 | 5000 | 5000 | 5000 | 15000 | 15000 | 0 | 0 | 0 | 0 | 507250
2.11 | Institutional capcity development in governace,data system,leadership and monitoring and evaluation (leadership and Management workshop)
2.11.1 | Catering services, logistics, venues, stationery, etc., for holding training | 2300 | 0 | 2300 | 0 | 0 | 2300 | 2300 | 0 | 240000 |  | 240000 | -6665
2.11.2 | Travel, accommodation, per diem for five facilitators/ consultants holding 3 days training | 6000 | 0 | 6000 | 0 | 0 | 6000 | 6000 | 0 | 78900 |  | 78900 | 529800
2.11.3 | …………………………………………………………………………………………………………………….. | 5030 |  | 5030 | 0 |  | 5030 | 0 | 5030 | 700368 |  | 700368 | -190074.5
2.11.4 | stationary | 100 |  | 100 |  |  | 100 | 100 |  |  |  | 0 | 10145
| SUB-TOTAL | 13430 | 0 | 13430 | 0 | 0 | 13430 | 8400 | 5030 | 1019268 | 0 | 1019268 | 343205.5 | 74.81%
| TOTAL ACTIVITY 2 | 273675 | 0 | 137350 | 102025 | 40800 | 273675 |  |  | 2502158 | 0 | 2502158 | 11431999.5 | 17.96%
3.1 | Cultural Seminars and language training
3.1.1 | Orientation /cultural seminars expense in terms of meals, transport, perdiem | 1000 | 0 | 1000 | 0 | 0 | 1000 | 1000 | 0 | 87700 |  | 87700 | 13750
3.1.2 | Language training | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| SUB-TOTAL | 1000 | 0 | 1000 | 0 | 0 | 1000 | 1000 | 0 | 87700 | 0 | 87700 | 13750 | 86.45%
3.5 | Visiting professors/external expertise
3.5.1 | Support of professors/external expertise to PTRE (Travelling cost and Perdiem) | 10000 |  | 3000 | 3500 | 3500 | 10000 | 10000 | 0 | 0 | 0 | 0 | 304350
| SUB-TOTAL | 10000 | 0 | 3000 | 3500 | 3500 | 10000 | 10000 | 0 | 0 | 0 | 0 | 304350 | 0%
3.6(b) | Development of a new MSc program in phytochemistry
3.6.1b | Travel, accommodation, per diem, catering services on development of at least 1 curriculum | 2000 | 0 | 1000 | 1000 | 0 | 2000 | 2000 | 0 |  |  | 0 | 101450
3.6.2b | Accreditation cost | 2000 | 0 | 0 | 0 | 2000 | 2000 | 2000 | 0 |  |  | 0 | 0
| SUB-TOTAL | 4000 | 0 | 1000 | 1000 | 2000 | 4000 | 4000 | 0 | 0 | 0 | 0 | 101450 | 0%
3.7 | Benchmarking with partnership of Applied Sciences,Engineering and Technology (PASET) and partners for peer review for accreditation
3.7.1 | Bench-marking seminars /workshop for the relevant thematic areas | 1000 | 0 | 0 | 1000 | 0 | 1000 | 1000 | 0 |  |  | 0 | 0
3.7.2 | Peer review with partners for accreditation of programs offered at the center and for development of new programs | 11000 | 0 | 0 | 11000 | 0 | 11000 | 11000 | 0 |  |  | 0 | 0
3.7.3 | Cost of materials for benchmarking (stationary) | 100 |  |  | 100 |  | 100 | 100 |  |  |  | 0 | 0
| SUB-TOTAL | 12100 | 0 | 0 | 12100 | 0 | 12100 | 12100 | 0 | 0 | 0 | 0 | 0
0
| TOTAL ACTIVITY 3 | 27100 | 0 | 5000 | 16600 | 5500 | 27100 |  |  | 87700 | 0 | 87700 | 419550 | 17.29%
4.1 | Upgrade of of Textile labaratory and Phytochemical research labaratory ,renewable energy and generator back up
4.1.1 | Dyeing machines | 40000 | 0 | 40000 | 0 | 0 | 40000 | 40000 | 0 |  |  | 0 | 4058000
4.1.2 | Textile HP-HT Kier boiler | 25000 | 0 | 25000 | 0 | 0 | 25000 | 25000 | 0 |  |  | 0 | 2536250
4.1.3 | IDRaman mini Handheld Raman Spectrometer | 25000 | 0 | 25000 | 0 | 0 | 25000 | 25000 | 0 |  |  | 0 | 2536250
4.1.4 | Desktop SEM (JEOL JCM-6000 Neoscope) | 20000 | 0 | 20000 | 0 | 0 | 20000 | 20000 | 0 |  |  | 0 | 2029000
4.1.5 | Electrical Muffle Furnace | 1500 | 0 | 1500 | 0 | 0 | 1500 | 1500 | 0 |  |  | 0 | 152175
4.1.6 | Auto hot press machine (Hotonix STX20) –controlled pressure | 1005 | 0 | 1005 | 0 | 0 | 1005 | 1005 | 0 |  |  | 0 | 101957.25
4.1.7 | Powdering/grinding machine | 800 | 0 | 800 | 0 | 0 | 800 | 800 | 0 |  |  | 0 | 81160
4.1.8 | Forced Ventilation Oven | 730 | 0 | 730 | 0 | 0 | 730 | 730 | 0 |  |  | 0 | 74058.5
4.1.9 | Absorbance tester –Lamotte | 600 | 0 | 600 | 0 | 0 | 600 | 600 | 0 |  |  | 0 | 60870
4.1.10 | Electronic thermometer | 500 | 0 | 500 | 0 | 0 | 500 | 500 | 0 |  |  | 0 | 50725
4.1.11 | Digital verniercaliper | 500 | 0 | 500 | 0 | 0 | 500 | 500 | 0 |  |  | 0 | 50725
4.1.12 | Strain gauges | 300 | 0 | 300 | 0 | 0 | 300 | 300 | 0 |  |  | 0 | 30435
4.1.13 | High pressure stainless steel boiler | 400 | 0 | 400 | 0 | 0 | 400 | 400 | 0 |  |  | 0 | 40580
4.1.14 | Cutting machine –Octo Round Knife | 750 | 0 | 750 | 0 | 0 | 750 | 750 | 0 |  |  | 0 | 76087.5
4.1.15 | Solar Module Quantum efficiency measurement system (with all accessories) | 60000 | 0 | 60000 | 0 | 0 | 60000 | 60000 | 0 |  | 0 | 0 | 6087000
4.1.16 | THERMO NICOLET NEXUS 870 FTIR ESP FT-IR Spectrometer | 12000 | 0 | 12000 | 0 | 0 | 12000 | 12000 | 0 |  |  | 0 | 1217400
4.1.17 | Shimadzu LC-2010 CHT HPLC | 58421 | 0 | 58421 | 0 | 0 | 58421 | 58421 | 0 |  |  | 0 | 5926810.45
4.1.18 | Heidolph™ Hei-Vap™ Rotary Evaporator | 9450 | 0 | 9450 | 0 | 0 | 9450 | 9450 | 0 |  |  | 0 | 958702.5
4.1.19 | compound microscope with CAMERA | 15000 | 0 | 15000 | 0 | 0 | 15000 | 15000 | 0 |  |  | 0 | 1521750
4.1.20 | Flash point module | 7000 | 0 | 7000 | 0 | 0 | 7000 | 7000 | 0 |  |  | 0 | 710150
4.1.21 | PECVD split tube furnace systems | 15000 | 0 | 15000 | 0 | 0 | 15000 | 15000 | 0 |  |  | 0 | 1521750
4.1.22 | 2000 PV Modules | 5000 | 0 | 5000 | 0 | 0 | 5000 | 5000 | 0 |  |  | 0 | 507250
4.1.23 | Diesel / LPG burner system | 8000 | 0 | 8000 | 0 | 0 | 8000 | 8000 | 0 |  |  | 0 | 811600
4.1.24 | PV Array Combiner Boxes | 1500 | 0 | 1500 | 0 | 0 | 1500 | 1500 | 0 |  |  | 0 | 152175
4.1.25 | Fuses and Breakers | 200 | 0 | 200 | 0 | 0 | 200 | 200 | 0 |  |  | 0 | 20290
4.1.26 | Automatic biodiesel oil oxidation stability analyzer, oil laboratory testing equipment. | 10000 | 0 | 10000 | 0 | 0 | 10000 | 10000 | 0 |  |  | 0 | 1014500
4.1.27 | Support of partners to upgrade laboratories | 10000 | 0 | 10000 | 0 | 0 | 10000 | 0 | 10000 |  |  | 0 | 1014500
| SUB-TOTAL | 328656 | 0 | 328656 | 0 | 0 | 328656 | 318656 | 10000 | 0 | 0 | 0 | 33342151.2 | 0%
4.2 | Laboratory equipment installation, commissioning and training
4.2.1 | Installation of laboratory equipment | 4000 | 0 | 0 | 4000 | 0 | 4000 | 4000 | 0 |  |  | 0 | 0
4.2.2 | Commissioning of laboratory equipment | 4000 | 0 | 0 | 0 | 4000 | 4000 | 4000 | 0 |  |  | 0 | 0
4,2,3 | Training of Technicians on use of new equipment’s | 2000 | 0 | 0 | 2000 | 0 | 2000 | 2000 | 0 |  |  | 0 | 0
| SUB-TOTAL | 10000 | 0 | 0 | 6000 | 4000 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0
4.4 | Purchase of labaratory consumables and softwares
4.4.1 | Laboratory consumables (textile materials, chemicals reagents, safety clothing, glassware) | 15000 | 0 | 10000 | 5000 | 0 | 15000 | 15000 | 0 |  | 501190 | 501190 | 513310
4.4.2 | VASP code | 3000 | 0 | 0 | 3000 | 0 | 3000 | 3000 | 0 |  |  | 0 | 0
4.4.3 | Atomistic Tool Kit-Virtual Nano Lab licence | 4000 | 0 | 0 | 4000 | 0 | 4000 | 4000 | 0 |  |  | 0 | 0
| SUB-TOTAL | 22000 | 0 | 10000 | 12000 | 0 | 22000 | 22000 | 0 | 0 | 501190 | 501190 | 513310 | 49.4%
4.7 | Establish new partnerships (MOUs) and strengthen existing ones in the area of teaching & research
4.7.1 | Support of faculty and ACE team to establish Memorundum of Understandings with partners (Travelling cost and Perdiem) | 20000 | 0 | 10000 | 10000 | 0 | 20000 | 20000 | 0 | 316475 |  | 316475 | 698025
| SUB-TOTAL | 20000 | 0 | 10000 | 0 | 0 | 20000 | 20000 | 0 | 316475 | 0 | 316475 | 698025 | 31.2%
4.8 | Faculty /PhD student Mentorship on specialised skills (internships,mobility)
4.8.1 | Support of staff mobility to public and private sector institutions of higher learning and industry (Travelling cost and Perdiem) | 30000 | 0 | 10000 | 10000 | 10000 | 30000 | 30000 | 0 | 356069 | 52950 | 409019 | 605481
4.8.2 | Support partners to mentorship logistics/mobility (Travelling, Perdiem, communication, stationeries, venues, consultancy cost, training cost) | 3500 | 0 | 0 | 3500 | 0 | 3500 | 0 | 3500 |  |  | 0 | 0
| SUB-TOTAL | 33500 | 0 | 10000 | 13500 | 10000 | 33500 | 30000 | 3500 | 356069 | 52950 | 409019 | 605481 | 40.32%
4.9 | Support faulty to submit Grant proposals
4.9.1 | Grant application logistics (Travel, Perdiem, communication, stationeries, venues, consultancy cost) | 5000 | 1000 | 2000 | 2000 | 0 | 5000 | 5000 | 0 | 0 | 0 | 0 | 304350
| SUB-TOTAL | 5000 | 1000 | 2000 | 2000 | 0 | 5000 | 5000 | 0 | 0 | 0 | 0 | 304350 | 0%
4.11 | Faculty/Students collaborative research
4.11.1 | Research activities logistics (Travel, Perdiem, communication, stationeries, venues, consultancy cost, materials, insurance ) | 10000 | 0 | 0 | 5000 | 5000 | 10000 | 10000 | 0 |  |  | 0 | 0
4.11.2 | Support partners students in research | 2000 |  | 0 | 0 | 2000 | 2000 | 0 | 2000 |  |  | 0 | 0
| SUB-TOTAL | 12000 | 0 | 0 | 5000 | 7000 | 12000 | 10000 | 2000 | 0 | 0 | 0 | 0
4.12 | Participation in external seminar workshop, conference and short courses
4.12.1 | Professional skills training and conference attendance logistics (Travel, Perdiem, communication, stationeries, publication, visas, insurance ) | 10000 | 0 | 5000 | 5000 | 0 | 10000 | 10000 | 0 |  |  | 0 | 507250
4.12.2 | support partners to seminar workshop, conference and short courses | 3200 |  | 1200 | 2000 | 0 | 3200 | 0 | 3200 |  |  | 0 | 121740
| SUB-TOTAL | 13200 | 0 | 6200 | 7000 | 0 | 13200 | 10000 | 3200 | 0 | 0 | 0 | 628990 | 0%
4.14 | Maintain ,insurance and service research vehicles (4X4 vehicles,Minibus)
4.14.1 | Vehicle Insurance –Mini bus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.14.2 | Vehicle service and maintenance – Mini bus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.14.3 | Vehicle Insurance – 4x4 extended land cruiser | 2000 | 0 | 2000 | 0 | 0 | 2000 | 6000 | 0 |  |  | 0 | 202900
4.14.4 | Vehicle service and maintenance – 4x4 land cruiser | 1500 | 0 | 500 | 500 | 500 | 1500 | 1000 | 0 |  |  | 0 | 50725
4.14.5 | Local and regional travel (Fuel and Perdiem) | 6500 | 0 | 2000 | 2500 | 2000 | 6500 | 3000 | 0 |  |  | 0 | 202900
| SUB-TOTAL | 10000 | 0 | 4500 | 3000 | 2500 | 10000 | 10000 | 0 | 0 | 0 | 0 | 456525 | 0%
4.16 | Procurement of 4X4 extended land cruiser vehicle for ACE centre field activities and meetings
4.16.1 | Purchase of one 4x4 extended double cabin pick-up | 74000 | 0 | 74000 | 0 | 0 | 74000 | 74000 | 0 | 7400000 | 0 | 7400000 | 107300
| SUB-TOTAL | 74000 | 0 | 74000 | 0 | 0 | 74000 | 74000 | 0 | 7400000 | 0 | 7400000 | 107300 | 98.57%
4.18 | Trainings, benchmarks and exchange for Center accountant, procurment, administrator, social and environmentl safeguard officer and support staff working under ACE
4.18.1 | Support for training i.e fees for course, perdiem, transport, air ticket) | 5000 | 0 | 4000 | 1000 | 0 | 5000 | 5000 | 0 | 370200 |  | 370200 | 35600
| SUB-TOTAL | 5000 | 0 | 4000 | 1000 | 0 | 5000 | 5000 | 0 | 370200 | 0 | 370200 | 35600 | 91.23%
| TOTAL ACTIVITY 4 | 533356 | 1000 | 449356 | 49500 | 23500 | 533356 |  |  | 8442744 | 554140 | 8996884 | 36691732.2 | 19.74%
6 | Observation of best practices in ACE financial operation
6.1.0 | Financial reporting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.2.0 | Financial audit | 500 | 0 | 0 | 0 | 500 | 500 | 500 | 0 |  |  | 0 | 0
6.3.0 | Transparent financial management enhancement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.4.0 | Students sponsors refunds processing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| TOTAL ACTIVITY 6 | 500 | 0 | 0 | 0 | 500 | 500 | 500 | 0 | 0 | 0 | 0 | 0
7 | Observation of best practices in ACE procurement operation
7.1.0 | Procurement audit | 500 | 0 | 0 | 0 | 500 | 500 | 500 | 0 |  |  | 0 | 0
7.2.0 | Ensuring transparent procurement process | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| TOTAL ACTIVITY 7 | 500 | 0 | 0 | 0 | 500 | 500 | 500 | 0 | 0 | 0 | 0 | 0
| TOTAL ALL ACTIVITIES | 1098831 | 32750 | 762456 | 165175 | 85950 | 1098831 | 931381 | 167450 | 19349557 | 554140 | 19903697 | 62697501.7 | 25.73%
| 1% CONTINGENCY | 10988.31 | 327.5 | 7624.56 | 1651.75 | 859.5 | 10988.31
| GRAND TOTAL | 1109819.31 | 33077.5 | 770080.56 | 166826.75 | 86809.5 | 1109819.31
Verified by: Project Accountant………………………K CHIRCHIR………………………………………………….
| Approved by: Centre Leader ACE II PTRE……………………………………………………… |  |  | Date:………………………
| Approved by: VICE CHANCELLOR………………………………………………………………… |  |  | Date:………………………
% USED PAID
% USED (PAID & COMMITTED)