## Annual_work_program_2018_2019
EASTERN AND SOUTHERN AFRICA CENTERS OF EXCELLENCE (ACE II)
| Name of the ACE: |  | CENTER OF EXCELLENCE IN PHYTOCHEMICALS, TEXTILE AND RENEWABLE ENERGY (PTRE) | [9 empty] | Year 2018/2019
July 2018 - June 2019
Activity Number | Component | Sub- component | Action Plan | Objective | Justification | Output | DLI # | DLR # | Estimated Budget (US$) | Component total ACE LEADER | (Component total partners) | Responsible Unit | July | August | september | October | November | December | January | February | March | April | May | June
1 | Achieving excellence in training | Supporting institutional frame work for delivery of ACE activities | Improvement of Center facilities | i) Purchase centre’s training facilities ii) Provide secure doors in ACE bulidings to guard purchased equipments | For continous functioning of centre of excellence, the centre needs training facilities. The center need to also secure PTRE purchased equipments | • Acquisition of center’s training facilities • Improve faculty office funiture • Maintainance of centers buildings | DLI #2 | DLR# 2.1 | 25000 | 25000 | 0 | Center leader, ACE Team, procurement officer, finance officer
2 |  |  | Conduct seminars for self evaluation of project progress and industrial linkage committee meeting | i) To conduct project self evaluation seminars ii) hold two (2) industrial linkage committee meetings) This will need; • Material for project self evaluation seminar and industrial linkage meeting • Travel, accommodation, perdiem, catering services and venue for stakeholders for two (2) industrial linkage workshop offered • Travel, accommodation, per diem, catering services and venue for project team for self evaluation and team bulding (2) day workshops offered | • This is necessary to monitor the progress of project's activities and identify avenues for further improvement • To strengthen and build team work working relationship among project coordinators and university units • To strengthen working relationship with the industries and brain storm student and staff internship | Conduct seminars on self evaluation and have meetings with the industries. • two (2) stakeholders (external) Industrial linkage committee meeting done for provision of internship for postgraduate • One (1) self evaluation and team building seminar done. This will target the ACE PTRE team and university management | DLI #2 | DLR# 2.1 | 18000 | 18000 | 0 | Center leader, Deputy Centre Leader, Project coordinators Industrial linkage committee
3 |  |  | Plan and hold ACE implementation meetings and school postgraduate meetings to discuss students progress | i) Organize ACE meeting with coordinators ii) Hold school graduate faculty meetings to discuss students progress •This will need meals, toner, printing papers | Meetings helps in discussing progress of ACE project as well as planning for activities Graduate faculty meetings helps discuss students progress | i) Hold at least six (6) ACE meetings ii) Hold at least six (6) graduate faculty meetings | DLI #2 | DLR# 2.1 | 5000 | 5000 | 0 | Center leader, Center administrator
4 |  |  | Partners annual meeting | i) To hold an annual meeting between PTRE team members from moi university and national, regional and international partners. This will need • Meeting venues, road transport, air tickets, meals, per diem, accommodation and stationery | Meetings helps in discussing PTRE annual workplan and progress of implimentation of planned activities | One (1) annual joint partners meeting held. This will be attended by regional partners (Busitema university, Gezira university, national university of science and technology, University of South Africa) National partners (KIRDI, Flexi biogas, AEPEA, RIVATEX, KAM and community representative) and PTRE ACE team and University management | DLI #2 | DLR# 2.1 | 25000 | 15000 | 10000 | Center leader, Deputy Center Leader
5 |  |  | Operation Cost | i) Enable smooth running of PTRE ii) Conduct evaluation of courses for programmes offered in the centre iii) Analyze data obtained from the course evaluation iv) Draft progress report on centre activities: teaching and research This will need; Printing papers, toner v) Airtime for running the ACE vi) facilitate traveling to ACE meetings organized by the IUCEA and World Bank | Necessary for smooth running of ACE activities | Have PTRE activities undertaken | DLI #2 | DLR# 2.1 | 40000 | 40000 | 0 | Center Leader
Subtotal |  |  | SUB TOTALS | [5 empty] | 113000 | 103000 | 10000
6 |  | Strengthen education capacity excellence - quality and productivity | Gender sensitization on postgraduate training in the areas of STEM related to PTRE | i) Enhanced knowledge on gender awareness and gender sensitivity on postgraduate programs choices available in STEM fields under PTRE. ii) Full and equal participation of female students shall be promoted through one open forum day iii) Increased number of female students enrolled in PhD and MSc programs • Printing of sensitization material and provision of meals for sensitization team and participants • Travel, accommodation, per diem for attending open forums in other universities | Necessary to increase the number of females enrolling for postgraduate | • Hold one (1) gender sensitization training in PTRE on postgraduate studies •Attend one (1) open forums in other universities or institutions to enhance gender awareness on postgraduate training in PTRE | DLI #2 | DLR# 2.1 | 2500 | 2500 | 0 | Center Leader, Deputy Center Leader, Coordinators, Moi University Institute of Gender Equity, Research and Development
7 |  |  | Advertisement of activities | i) Generate high quality applications into PhD and MSc programs through; • Advertisement of ACE postgraduate programs in print media (i.e., local newspapers, brochures, etc.) • Partner advertisement of ACE activities •Advertisement of tenders for supplies needed in PTRE | • This will Increase number, quality and diversity of students admitted into PhD and MSc programs • Raise awareness of PTRE center of excellence | • Call for application posted in the media or websites • Supplies tenders put on print media | DLI #2 | DLR# 2.1 | 5000 | 5000 | 0 | Center leader, GSREC, School Graduate Studies Committee (SGSC), Administrative officer, Thematic Program coordinators
8 |  |  | MSc Fellowships | i) To Enroll students and run MSc The fellowship will provide either accomodation, fees, research, medical payable to university, stippen | • Increase highly skilled personnel in the area of STEM, that will facilitate manufacture of skill-intensive products of high value and quality. | • Seventeen (17) new MSc students enrolled (partial and fully funded); 11 national (4F 36%) and 6 (35%) regional MSc students (2F 33%) . They will be distributed as follows; MSc Analytical chemistry (4), MSc Textile Engineering (4), MSc Industrial Engineering (4), MSc Energy studies (5) •This will support continuing MSc students in MSc Renewable energy; 2 regional male, 1 national male and 1 national female. MSc industrial engineering; 1 male regional student, 2 national male, 2 national female and 2 national female. MSc textile; 3 regional male, 1 national male, and 1 national female. Msc analytical chemistry; 2 regional female, 3 national male, 4 national male. • Support 10 MSc (energy student, textile and industrial engineering) and 2 PhD (energy studies)students for at least 1 month internship to industry | DLI #2 | DLR# 2.2 | 75845 | 21925 | 53920 | Center leader and Deputy Center leader, Coordinator MSc and PhD programs
9 |  |  | PhD Fellowships | i) To Enroll students and run PhD The fellowship will provide either accomodation, fees, research, medical payable to university, stippen | • This will Increase highly skilled personnel in the area of STEM, that will facilitate manufacture of skill-intensive products of high value and quality. | •Fifteen(15) new PhD students enrolled (partial and fully funded). 10 national PhD students (3 F 30% and 7 male) and 5 regional PhD students (2 F 40% and 3 male). They will be distributed in PhD Analytical Chemistyr (5), PhD Materials and Textile Engineering (5), PhD Energy studies (5) •This will support continuing PhD students PhD analytical chemistry; 1 regional male, 2 regional female, 1 national female and 2 national male. PhD material and textile engineering; 1 regional female, 2 regional male, 4 national male and 1 national female. PhD energy studies; 1 regional male and 1 national male. | DLI #2 | DLR# 2.2 | 93900 | 13800 | 80100 | Center leader and Deputy Center leader, Coordinator MSc and PhD programs
10 |  |  | ICT Upgrading and E resource purchase | i) To enhance learning environment to facilitate communication through; • Install projectors & Smart white boards, • Provide Internet connectivity • Increase Internet Bandwidth (20 Mbps) • Purchase projectors, laptops, & printers • The centre shall procure; Internet access equipment, antivirus for computers • To subscribed e-resources (international journals, books and databases) ii) To train faculty staff in PTRE and postgraduate students on availability and use of e-resourses | • This will create highly versatile education, research and training environments that can provide equal access to information • This will create access to a wide range of upto date research findings • This will solve the challenge of accesseing journal articles and e-books that are restricted | • Teaching rooms installed with projectors and Smart board interactive White boards. • Increased internet connectivity, speed and access established • Subscription to e-resources • Faculty staff and postgraduate students trained on use of e-resources | DLI #2 | DLR# 2.1 | 45000 | 45000 | 0 | Center Leader, Deuty center leader, Coordinators, Center adminsitrator, University ICT Director
|  |  | Re-tool faculty in areas relevant to the ACE | To enhace faculty skills | this will improve service delivery in the Center | facilitation of faculty and support staff for re tooling | DLI #3 | DLR# 2.2 | 20000 | 20000 | 0
12 |  |  | Develop short courses curricullum | i) To develop two (2) short courses This will need; • Travel, accommodation, per diem, catering services, and venue for key stakeholders on development of short courses | • To support training needs. •To build capacity within Center, industries, institutions of higher learning and to those who require hands on skills | • At least two (2) short courses developed; 1 in energynthematic area and 1 in dyes (textile) | DLI #2 | DLR# 2.1 | 6500 | 6500 | 0 | Center leader, Deputy Center Leader coordinator short courses and internship and ACE team
13 |  |  | Offer short courses and seminars | i) To offer short courses developed This will need; • Catering services, logistics, venues, stationery, for holding training • Travel, accommodation, per diem for facilitators of short course and support of partners to short course | •To build capacity within Center and in partners, industries, institutions of higher learning •To build capacity/provide hands on skills for people who require enterprenuership skills • To offer short course jointly with partners | • At least two (2) short courses offered; 1 in certified energy management and 1 in dyes to achieve a total number of 60 participants trained. | DLI #2 | DLR# 2.1 | 15000 | 15000 | 0 | Center leader, coordinator short courses and internship and ACE team
SUB TOTALS | SUB TOTALS |  | SUB TOTALS | [5 empty] | 263745 | 129725 | 134020
14 |  | Education Capacity & Development Impact | Cultural seminars and language training | i) To perform Orientation to students ii)To provide English language training for students who have challenge in using english. •The Center shall need Stationary, Catering services, venue, facilitators, transport •The center shall pay language instructors | •To enable smooth integration of regional students to Moi University community •To equip students with new life skills for improved and productive residency | • One (1) Tour orientation of students on campus and eldoret town done • Language training provided to students with challenges in english | DLI #2 | DLR# 2.1 | 4500 | 4500 | 0 | Center leader, Coordinator seminars, ACE team
15 |  |  | Support of professors/external expertise to PTRE (Travelling cost and Perdiem) | i) Support of professors/external expertise to visit PTRE •This shall need Travelling cost and Perdiem | •To enable and support of professors/external expertise to PTRE for exchange of ideas and improve teaching, research activities | •Provision of ticket and Perdiem provision for at least 5 visiting professor to PTRE | DLI #2 | DLR#2.6 | 41000 | 5000 | 36000 | Center leader
|  |  | Review of curriculums and national accreditation | i) Support facaulty in the review of a curriculum tonational level This shall need •Provision for travel, per diem, catering services • provision of accreditation cost | To enable quality of PTRE curriculum acquire national accreditation | •At least 2 (1 MSc energy studies and 1 Phd energy studies) curriculum | DLI #2 | DLR#2.3 | 5000 | 5000 | 0 | Center leader/coordinators
16 |  |  | Regional/ International accreditation of curriculum | i) Support facaulty in the review of a curriculum to international level This shall need •Provision for travel, per diem, catering services • provision of accreditation cost | To enable quality of PTRE curriculum acquire regional quality and standards | At least one (1) curriculum accreditted to regional level | DLI #2 | DLR#2.3 | 15000 | 15000 | 0 | Center leader, Coordinator
|  |  | Develop New Curriculum | Support faculty in development and accreditation of a new curriculum in MSc phytochemistry | To enable quality of PTRE curriculum | At least one (1) new curriculum developed and accredited |  |  | 5000 | 5000 | 0 | Center leader, Coordinator
17 |  |  | Benchmarking with Partnership of Applied Sciences,Engineering and Technology (PASET) and partners for peer review for accreditation | i) To undertake bench-marking activities for the relevant thematic areas to include staff exchange, research, curriculum review and offering of short course | • Improve excellence through staff exchange to PASET Centers and working in joint activities • Have programs that meet both national/international standards, besides meeting market demands | • Long term Improvements in academic/research standards in the region | DLI #2 | DLR#2.8 | 10000 | 10000 | 0 | Center leader, ACE team
SUB TOTALS | SUB TOTALS |  | SUB TOTALS | [5 empty] | 80500 | 44500 | 36000
18 |  |  | Upgrade of teaching and research laboratory | i) To upgrade research laboratories for textile, phytochemical & renewable energy at the Centre | This is necessary; • To enhance quality of scientific research at postgraduate level both at the Center and in the partnering institutions • | • Procured teaching and research equipments as in procurement plan • Improved laboratories infrastructure | DLI #2 | DLR# 2.1 | 373000 | 373000 | 0 | Center leader, procurement officer, finance officer, Coordinators phytochemicals, textile and renewable energy,
|  |  | Labaratory equipment installation, commissioning and training | To ensure that the equipments are in use | To enhance quality of teaching and research | to install labaratory equipment | DLI #2 | DLR# 2.1 | 7000 | 7000 | 0 | Center leader, procurement officer, finance officer, Coordinators phytochemicals, textile and renewable energy,
|  |  | Generator Back up | Purchase of generator back up Generator back up | To ensure uninterrupted power supply at Center laboratories | • Improved laboratories infrastructure | DLI #3 | DLR# 2.2 | 70000 | 70000 | 0 | Center leader, procurement officer, finance officer, Coordinators phytochemicals, textile and renewable energy,
|  |  | Maintain, service and calibrate academic infrastructure/facilities for learning and research | i) To maintenance of research equipments ii) To service research equipments iii) To calibrate research equipments | • This is necessary to ensure proper working of equipment and authentic research results | • Long term proper working of equipment | DLI #2 | DLR# 2.1 | 10000 | 10000 | 0 | Center leader, procurement officer, finance officer, Coordinators phytochemicals, textile and renewable energy,
|  |  | Purchase of laboratory consumables and software’s | To acquire laboratory consumables and computer software | • To avail necessary chemicals and computer software for the commencement of postgraduate research | • Procured laboratory consumables for Analytical chemistry, textile and Renewable energy • Procured software • Renewed software licenses | DLI #2 | DLR# 2.1 | 60000 | 60000 | 0 | Center leader, procurement officer, Coordinators phytochemicals, textile and renewable energy
|  |  | Establishment of biogas unit | To enhance teaching and research in renewable energy | To ensuer effective demonstrations are done on biogas production | Improved training facilities | DLI #4 | DLR# 2.3 | 20000 | 20000 | 0 | Center Ledear, Coordinator renewable energy, coordinator social and environmental safeguards
22 |  |  | Outreach services to remote areas/marginalized areas and in surrounding community | i) To provide skill based outreach training services in PTRE thematic areas to remote areas ii) To raise awareness of ACE activities in marginalized and remotes areas and create gender awarness | • To build capacity in remote • To increase number of postgraduate students from remote/marginalized areas | Engagement of communities in remote areas/marginalized areas in PTRE activities through 2 outreach activities in renewable energy and textile | DLI #2 | DLR# 2.1 and 2.2 | 10000 | 10000 | 0 | Center Leader, Deputy center Leader, PTRE Coordinators
23 |  |  | Establish new partnerships (MOUs) and strengthen existing ones in the area of teaching & research | i) Support of faculty and ACE team to establish Memorundum of Understandings with partners ii) The Center shall need Travelling cost and Perdiem, catering,venue and stationary | • This is necessary to enhance delivery learning, research and extension at the Center • It will enable provision for places of internships , faculty/PhD students exchange | At least two (2) MOUs signed between; PTRE Center and 1 public institutions/civil society and 1 private sector/industry | DLI #2: | DLR#2.4 | 2000 | 2000 | 0 | Center leader, Deputy Center leader, Coordinators
24 |  |  | Faulty /PhD student Mentorship on specialised skills (internships,mobility/exchange) | • To facilitate acquisition of specialised skills by faculty/PhD students • To expose faculty/PhD students to various learning/research environments | This is necessary; • For impacting the required skills to faculties/PhD students for enhancement of their teaching/researching, • For exposing faculties/PhD students to various learning/researching environments related to their areas of specialisation. | • Faculty/PhD students acquisition of specialised skills as per the staff development plan | DLI#2 | DLR#2.6 | 68000 | 58000 | 10000 | Center leader, Deputy center Leader, Coordinators
25 |  |  | Support faculty to submit Grant proposals | To facilitate grant applications by faculties | This is necessary for the sustainabilty of the Center through new grants and also for ensuring continued reaserch at the Centre. | i) Establishment of new research projects in Phytochemistry, textile and Renewable energy ii) Submitted grant proposals for advertised calls iii) Money, labaratory equipment or other forms of facilitation received into ACE | DLI #2 | DLR#2.4 and DLR#2.7 | 8000 | 8000 | 0 | Center Leader
26 |  |  | Faculty/Students collaborative research | • To establish research groups from each of the thematic area of the Center • To facilitate faculties to publish in peer review journals | This is necessary; • To ensure continued research that is relevant to the Center partners • To improve the visibility of the Centre to outside world through publications | • Operational research group offering research topic to prospective postgraduate students in Phytochemistry, textile and renewable energy • research output leading to faculty and postgraduate publications in peer review journals | DLI #2 | DLR#2.5 and 2.7 | 120000 | 60000 | 60000 | Center leader, ACE Team, procurement officer, finance officer
27 |  |  | Participation in external seminars, workshops, conferences and short courses | i) To disseminate research findings by the Center students and faculty ii) To acquire professional skills by the Center students and faculty ii) To network the Center students and faculty with other local and regional researchers | This is necessary; • To allow the Center students, PTRE faculty and partners to disseminate their research findings • To facilitate the Center students, faculty and partners to acquire professional skills necessary for their future careers • For networking between the Center students and other local and regional students • support partners to attend short courses | • Seminars, workshops and conferences attendance by the Center students, PTRE faculty or partners. • Presentations at seminar, workshops and conferences by the Center students, PTRE faculty or partners. • Center students or partners knowledgeable in specific professional skills • have partners participate in short courses offered at the PTRE • Support 5 PTRE faculty take short courses in skill gap areas as per the staff development plan • Support 2 PTRE faculty present in conferences as per the staff dvelopment plan | DLI #2 | DLR #2.2 | 15000 | 10000 | 5000 | Center leader, Coordinator seminars and workshop
28 |  |  | Publish research findings in peer-reviewed journals | i) To Publish research findings in and peer-reviewed journals • This will requier provision of open-source fee/publication fee | • This is necessary for the visibility of PTRE | •Published articles in peer-reviewed journals by the ACE students | DLI #2 | DLR #2.4 | 15000 | 10000 | 5000 | Center Leader, PTRE Coordinators
29 |  |  | Maintain, insurance and service research vehicles (4X4 vehicle), local and regional travel | i) To maintain, insure and service Centers vehicles ii) To facilitate local and regional travel to PTRE related inivations | • This is necessary for the operationalization of Center's vehicles in good order • This is necessary to achieve PTRE related activities where PTRE team members are invited | •Hitch travel/commuting using the Center vehicles •Participation in regional and national PTRE related activities | DLI #2 | DLR#2.1 | 15000 | 15000 | 0 | Center leader, procurement officer, finance officer
30 |  |  | Trainings, benchmarks and exchange for support staff working under ACE or units facilitating ACE | This will ensure effeciency and operations of activities in the ACE according to the expected standards | This is necessary to • enhance financial and procurement management • ensure efective performance of staff facilitating ACE activities | • Training skills improved for 9 staff supporting PTRE as per the staff development plan | DLI #2 | DLR# 2.1 | 14000 | 14000 | 0 | Center leader
SUB TOTALS | SUB TOTALS |  | SUB TOTALS | [5 empty] | 807000 | 727000 | 80000
31 |  | Observation of best practices in ACE financial operation | Observation of best practices in ACE financial operation | i) To write financial progress report ii)To perform financial audit iii) To ensure transparent financial management enhanced iv) To eusure students sponsors refunds processing | This is necessary for Carrying out financial audit at the end of the year, compile project funds used in the year and provide approved financial reports. | Audited and approved financial report provided Financial progress report provided | DLI #3 | DLR#3.1,DLR#3.2 DLR#3.3DLR#3.4 | 500 | 500 | 0 | Center leader, Deputy Center Leader, Center administrator Project accountant, Finance officer
SUB TOTALS | SUB TOTALS |  | SUB TOTALS | [5 empty] | 500 | 500 | 0
32 |  |  | Observation of best practices in ACE procurement operation | i) To perform Procurement audit ii) To Ensuring transparent procurement process iii) To write procurement progress report | This is necessary for Carrying out procurement activities audits by end of year, to compile the project items purchase procured in the year and provide approved procurement reports | Audited and approved procurement reports | DLI #4 | DLR# 4.1 DLR# 4.2 | 500 | 500 | 0 | Center leader, Deputy Center Leader, Center administrator, Center Procurement officer and University procurement officer
SUB TOTAL | SUB TOTAL |  | SUB TOTAL | [5 empty] | 500 | 500 | 0
GRAND TOTAL | GRAND TOTAL |  | GRAND TOTAL | [5 empty] | 1265245 | 1005225 | 260020